PHASE 5

Governed Agentic Security Platform on GKE

Plan Mode Project Summary and Implementation Guide

Google Cloud | GKE | Vertex AI / Gemini | OPA | Cloud KMS | MCP | GitHub Actions

Document purpose This document adapts the Cursor AI Plan Mode workflow to the complete Phase 5 repository. It captures clarified scope, research findings, file organization, implementation tasks, dependencies, risks, testing, success criteria, review gates, and the controlled deployment sequence.

| Project type | Student portfolio lab with production-minded architecture and security controls |
| --- | --- |
| Current status | Configuration-ready; live Google Cloud, GKE, KMS, policy, and release validation still required |
| Complexity | 9/10 - multi-service, event-driven, policy-governed Kubernetes platform |
| Safety posture | Fail-closed; remediation and external reporting disabled by default |
| Prepared by | T.I.Q.S. |

Prepared for technical review, recruiter discussion, and guided implementation

Phase 5 Network Architecture

(Coming Soon)

Figure 1. Governed multi-agent security workflow, trust boundaries, event topics, and supporting Google Cloud services.

# Document roadmap

| Section | Purpose |
| --- | --- |
| Phase 1 | Clarification - scope, requirements, constraints, goals, and success criteria |
| Phase 2 | Research - current-state assessment, component mapping, and design patterns |
| Phase 3 | Plan generation - structure, checklist, dependencies, risk, testing, and next steps |
| Phase 4 | Review - formal approval gate before controlled execution |
| Phase 5 | Implementation - deployment sequence, operational handoff, and validation |
| Appendix A | Major component summary and enterprise relevance |
| Appendix B | Reusable Cursor AI Plan Mode prompt for future changes |

Plan Mode rule No live remediation, production deployment, or irreversible infrastructure change should occur until the plan is reviewed, the required tests pass, and an authorized reviewer approves the action.

# Phase 1: Clarification

The original Plan Mode template begins by clarifying scope, technology, constraints, goals, dependencies, and blockers. For this project, those questions have been resolved as follows.

| Clarification area | Resolved requirement |
| --- | --- |
| Project scope | Build a governed, event-driven security automation platform on GKE. AI assists analysis but does not independently authorize or execute infrastructure changes. |
| Cloud and region | Google Cloud project class-6-5-tiqs; us-central1 / us-central1-a; GKE cluster vertex-agent-lab. |
| Core stack | Terraform, GKE, Workload Identity, Pub/Sub, Vertex AI/Gemini, OPA/Rego, Cloud KMS, Firestore, BigQuery, Secret Manager, Cloud Logging, Cloud Monitoring, Docker, GitHub Actions, Trivy, Syft, and Cosign. |
| Primary security objective | Enforce deterministic authorization, signed human approval, least privilege, mTLS, replay prevention, immutable releases, and durable evidence. |
| Target workload | Demo application and PostgreSQL in app01; the only controlled action is against explicitly allowlisted Kubernetes resources. |
| Current repository state | Canonical Phase 5 files are present; historical Phase 1-4 workflows and retired agents were removed from the minimal structure. |
| Default execution posture | Governance and remediation remain disabled until explicitly changed to controlled after review and validation. |
| Success definition | End-to-end findings reach an incident report, sensitive actions require valid governance and approval evidence, and no bypass path exists around MCP, mTLS, policy, or RBAC. |
| Known blocker | Live validation requires Google Cloud credentials, a reachable GKE control plane, a configured backend bucket, and installed policy/release tooling. |

## Clarification checklist

[x] Scope and in-scope services are documented.

[x] Google Cloud project, region, zone, and cluster naming are defined.

[x] The target Kubernetes namespaces and allowlisted workload are defined.

[x] Fail-closed defaults are documented.

[ ] Cloud KMS reviewer identities must be replaced with real Google identities.

[ ] The administrator workstation CIDR must be set in the ignored terraform.tfvars.

[ ] The production GitHub environment reviewer must be configured.

# Phase 2: Research

The research phase identifies the active files, dependency chain, architectural patterns, and likely failure points before implementation or redeployment.

## Current-state findings

| Area | Finding |
| --- | --- |
| Architecture | Multi-stage Pub/Sub pipeline with isolated analysis, governance, approval, remediation, and reporting roles. |
| Identity | Dedicated Kubernetes and Google service accounts mapped through Workload Identity; GitHub uses OIDC federation. |
| Governance | OPA/Rego policy produces DENY, NO_ACTION, PERMIT, or REQUIRE_APPROVAL. |
| Approval | Cloud KMS asymmetric signing binds the reviewer to a specific request, decision, expiry, and key version. |
| State | Firestore stores correlation windows, approval consumption, and execution idempotency state. |
| Execution boundary | Remediation Agent uses an mTLS client certificate to reach nginx MCP Gateway; MCP Server holds scoped Kubernetes RBAC. |
| Evidence | Cloud Logging and BigQuery retain governance, approval, remediation, and MCP evidence. |
| Reliability | Pub/Sub retry/DLQ, HPA, PDB, probes, resource limits, and Managed Prometheus metrics. |
| Supply chain | GitHub Actions, Trivy, Syft, Cosign, immutable digests, SBOMs, signatures, and attestations. |

## Dependency chain

Terraform foundation
  -> GKE + Workload Identity + Artifact Registry
  -> Pub/Sub + Firestore + KMS + BigQuery + monitoring
  -> Container image build and release evidence
  -> Namespaces + service accounts + RBAC
  -> MCP certificates and gateway
  -> Demo workload + scanners
  -> Event, analysis, governance, approval, remediation, reporting agents
  -> NetworkPolicies + PodMonitoring + HPA + PDB
  -> Smoke tests + signed approval test + controlled execution review

## Relevant repository areas

| Path | Responsibility |
| --- | --- |
| .github/workflows | CI validation and governed release workflow |
| docker | One build definition for each runtime image |
| docs | Runbook, architecture, and governance concepts |
| manifests | Kubernetes workloads, policies, reliability, observability, and deployment RBAC |
| policy | Conftest and OPA/Rego policies |
| python | Agent services, shared runtime utilities, tests, and dependencies |
| scripts | Build, deploy, validate, test, approval, certificate, and release automation |
| terraform | GCP foundation, IAM, messaging, state, governance, evidence, and monitoring |

# Phase 3: Plan generation

Implementation status legend [x] means implemented in the repository. [ ] means environment-specific, live-cloud, or approval work remains.

## 1. Overview and implementation objective

Complete and validate a portfolio-grade Phase 5 platform that demonstrates responsible agentic AI integration on Kubernetes. The implementation must prove that analysis, authorization, approval, execution, and evidence are separate controls and that the AI model cannot bypass deterministic governance.

## 2. Canonical file structure

agentic/
├── .github/workflows/          # Phase 5 CI and governed release
├── docker/                     # Runtime image definitions
├── docs/                       # Runbook, architecture, and concepts
├── examples/                   # Non-runtime classroom examples
├── helm/falco/                 # Falco values
├── manifests/                  # Kubernetes workloads and controls
│   ├── network-policies/
│   ├── observability/
│   ├── rbac/
│   └── reliability/
├── policy/                     # Conftest and OPA/Rego
├── python/                     # Services, shared modules, tests
├── scripts/                    # Build, deploy, approval, test, release
├── terraform/                  # Numbered Phase 5 GCP infrastructure
└── README.md

## 3. Detailed implementation steps

### Repository hygiene

[x] Keep only Phase 5 workflows and canonical runtime files.

[x] Keep .terraform.lock.hcl and exclude .terraform, state, local tfvars, credentials, certificates, and release evidence.

[x] Replace committed PostgreSQL credentials with a generated Secret workflow.

[ ] Remove orphaned or retired Dockerfiles and historical agents.

### Terraform and Google Cloud foundation

[ ] Configure the GCS backend and sanitized terraform.tfvars.

[ ] Provision VPC, subnet, GKE, node pool, Artifact Registry, and APIs.

[ ] Provision Pub/Sub topics, subscriptions, retry policies, and DLQ.

[ ] Provision agent identities and Workload Identity bindings.

[ ] Provision Firestore, KMS, BigQuery evidence, Secret Manager, and monitoring.

[ ] Review terraform plan before apply.

### Build and supply chain

[ ] Build the eleven Phase 5 images.

[ ] Scan repository and images for vulnerabilities, secrets, and misconfiguration.

[ ] Generate SPDX SBOMs.

[ ] Sign immutable digests and attach SBOM attestations.

[ ] Verify signature identity and attestation issuer.

### Kubernetes platform

[x] Create seven namespaces and labels.

[x] Apply service accounts and least-privilege RBAC.

[ ] Generate MCP server/client CAs and Kubernetes Secrets.

[ ] Deploy MCP Gateway, MCP Server, PostgreSQL, and demo application.

[ ] Deploy Event Aggregator and agent workloads.

[ ] Apply NetworkPolicies, HPA, PDB, PodMonitoring, quotas, and limits.

### Telemetry and AI analysis

[ ] Install Falco and deploy Trivy/Prowler scanner CronJobs.

[ ] Verify raw-security-events and security-findings ingestion.

[ ] Verify Observer and Correlation Agent outputs.

[ ] Verify Gemini-assisted analysis produces normalized analyzed-incidents.

### Governance and approval

[x] Mount and test remediation.rego.

[ ] Verify DENY, NO_ACTION, PERMIT, and REQUIRE_APPROVAL behavior.

[ ] Generate a Cloud KMS-signed approval decision.

[ ] Verify request hash, expiry, key version, reviewer, and replay protection.

### Remediation and evidence

[x] Keep execution mode disabled during dry-run tests.

[ ] Verify Remediation Agent independently validates governance evidence.

[ ] Verify mTLS trust and MCP target allowlists.

[ ] Verify Firestore prevents duplicate execution.

[ ] Verify remediation result, incident report, logs, metrics, and BigQuery evidence.

### Controlled activation

[ ] Obtain formal review approval.

[ ] Change governance and execution modes to controlled.

[ ] Run one allowlisted, reversible controlled action.

[ ] Confirm evidence and rollback behavior.

[ ] Return to disabled mode after the demonstration if continuous automation is not required.

## 4. Dependencies and prerequisites

| Dependency | Purpose |
| --- | --- |
| Terraform >= 1.10 | Infrastructure initialization, validation, plan, apply, and destroy |
| gcloud and kubectl | Authentication, Artifact Registry, GKE credentials, Pub/Sub, KMS, and Kubernetes operations |
| Docker + Buildx | Local multi-image build workflow |
| Python 3.11 + pytest | Agent runtime, helpers, tests, and secret generation |
| OPA + Conftest | Governance policy and Kubernetes policy validation |
| OpenSSL | MCP server and client certificate generation |
| Helm | Falco installation |
| Trivy, Syft, Cosign | Security scanning, SBOMs, signatures, and attestations |
| GitHub repository variables | WIF provider, release service account, project, cluster name, and cluster location |
| Authorized reviewers | Cloud KMS signer IAM and protected GitHub production environment |

## 5. Potential issues and mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| GKE control plane is unreachable | Deployment, security, or workflow failure | Update the workstation /32 CIDR in the ignored terraform.tfvars and reapply. |
| VS Code cannot resolve every GitHub Action | Deployment, security, or workflow failure | Treat it as an editor resolver/authentication/network issue; validate with GitHub-hosted runs or actionlint. |
| Existing default Firestore database conflicts with Terraform creation | Deployment, security, or workflow failure | Set manage_firestore_database=false and manage only the required fields and TTL configuration. |
| Artifact Registry cannot be destroyed | Deployment, security, or workflow failure | Delete all image packages and versions before terraform destroy. |
| Pub/Sub stage repeatedly fails | Deployment, security, or workflow failure | Inspect the consumer logs, IAM, message schema, and agent-events-dlq-sub. |
| Approval signature is rejected | Deployment, security, or workflow failure | Verify canonical JSON, request hash, exact key version, reviewer, expiry, and decision binding. |
| NetworkPolicy blocks a required service | Deployment, security, or workflow failure | Verify DNS, metadata server, Google API, MCP, Prometheus, and app01 PostgreSQL paths. |
| Duplicate execution | Deployment, security, or workflow failure | Use Firestore transactions and idempotency keys before invoking MCP. |
| Model response is malformed or unsafe | Deployment, security, or workflow failure | Reject malformed output; do not allow AI output to bypass OPA or deterministic application checks. |
| Certificate trust failure | Deployment, security, or workflow failure | Rotate mTLS material, verify SANs and CA mounts, and restart gateway, server, and remediation workloads. |

## 6. Testing strategy

| Test layer | Method | Acceptance result |
| --- | --- | --- |
| Static code | Python compileall and pytest | All tests pass with no import or syntax errors |
| YAML | Parse Kubernetes and workflow YAML | All documents parse successfully |
| Shell | bash -n against all scripts | No syntax errors |
| Terraform | fmt, init -backend=false, validate, reviewed plan | Configuration validates and plan matches intended resources |
| OPA | opa test policy/governance -v | All remediation policy tests pass |
| Conftest | Evaluate active Kubernetes manifests | No policy violations |
| Supply chain | Trivy, Syft, Cosign sign/verify | No gated findings; SBOM and verified signature exist for each digest |
| Kubernetes | Rollout status, probes, RBAC, NetworkPolicy checks | All workloads ready and only intended network/access paths are allowed |
| Event pipeline | Publish correlated findings and inspect final report | End-to-end incident report received |
| Governance | Dry-run REQUIRE_APPROVAL scenario | No unauthorized remediation occurs |
| Approval | KMS sign and Approval Agent verification | Valid approval accepted; expired/replayed/modified approvals rejected |
| Controlled action | One allowlisted reversible action | Action succeeds once, evidence is complete, and rollback is available |

## 7. Success criteria

[ ] Every agent uses a dedicated identity and only required permissions.

[ ] All event stages have retry and dead-letter handling.

[ ] Gemini assists analysis but cannot authorize or directly execute Kubernetes actions.

[ ] OPA produces deterministic decisions and policy version evidence.

[ ] Critical or policy-selected actions require a valid signed human approval.

[ ] Approval replay, expiry, request mutation, and duplicate execution are rejected.

[ ] Only the Remediation Agent can authenticate to the MCP gateway.

[ ] MCP Server RBAC is limited to the allowlisted app01 operations.

[ ] Every release has vulnerability results, an SBOM, a verified signature, and immutable digest evidence.

[ ] Cloud Logging, metrics, Firestore, Pub/Sub, and BigQuery provide traceable operational evidence.

[ ] The platform can be cleanly deployed, tested, disabled, rolled back, and destroyed.

## 8. Next steps

Replace placeholder reviewer and administrator network values in local configuration.

Run phase5-validate.sh with Terraform, OPA, and Conftest installed.

Review and apply the Terraform plan.

Build and release the image set with SBOMs and Cosign evidence.

Deploy Phase 5 with remediation disabled.

Run metrics, governance, pipeline, approval, and evidence tests.

Complete a formal review before enabling controlled mode.

Record screenshots, logs, plan output, and evidence for the portfolio demonstration.

## Time estimate and complexity

| Workstream | Estimate |
| --- | --- |
| Repository cleanup and local validation | 4-8 hours |
| Terraform review and cloud provisioning | 6-12 hours |
| Image build and release evidence | 4-8 hours |
| Kubernetes deployment and troubleshooting | 8-16 hours |
| Governance, approval, and controlled-action testing | 8-16 hours |
| Documentation and portfolio evidence | 4-8 hours |
| Student-lab total | Approximately 34-68 focused hours |
| Enterprise hardening beyond this lab | Approximately 12-20 weeks for a small cross-functional team |

Complexity rating: 9/10 The platform spans cloud infrastructure, Kubernetes networking and identity, event-driven services, AI analysis, policy enforcement, cryptographic approvals, observability, evidence retention, and secure release engineering.

## Security, compliance, and audit considerations

Separation of analysis, authorization, approval, and execution responsibilities.

Least-privilege IAM and namespace-scoped Kubernetes RBAC.

Signed reviewer decisions with an auditable KMS key version.

Evidence retention and data-classification review for logs, prompts, findings, and reports.

Secret values added outside Terraform and never committed to the repository.

Admission-time trust enforcement should be added for a Fortune 500 deployment.

Formal threat modeling, red teaming, DR, SLOs, and incident-response ownership are required for production.

## Multi-environment support

| Environment | Required differences |
| --- | --- |
| Development | Low-cost cluster, synthetic telemetry, automation disabled, short retention, developer reviewer. |
| Staging | Production-like policy, KMS, WIF, scanners, evidence, and approval tests; controlled actions against non-production workloads. |
| Production | Private/regional architecture, protected release environment, independent reviewers, admission enforcement, managed PKI, DR, SLOs, and formal change control. |

## Rollback strategy

Keep automation and execution disabled until the review gate passes.

Deploy immutable image digests so each workload can be rolled back to a known release.

Use kubectl rollout undo for application-level rollback where appropriate.

Revert governance and remediation modes to disabled immediately after an unexpected action.

Revoke or rotate the MCP client certificate if the execution identity is compromised.

Disable a KMS key version and remove signer IAM after approval compromise.

Use Terraform plans and state-aware changes for infrastructure rollback; do not manually edit managed cloud resources without reconciliation.

# Phase 4: Review

The implementation may proceed to live controlled execution only after an authorized reviewer accepts the plan and the evidence below is complete.

[ ] Repository contains only approved active files

[ ] No plaintext secrets, keys, state, tfvars, or generated credentials are committed

[ ] Terraform plan reviewed

[ ] Python, YAML, Bash, Terraform, OPA, and Conftest validation passed

[ ] Image scan, SBOM, signature, and attestation verification passed

[ ] All Deployments are ready and health checks pass

[ ] NetworkPolicy and RBAC negative tests pass

[ ] Governance dry-run returns REQUIRE_APPROVAL without execution

[ ] Cloud KMS approval is signed and verified

[ ] Replay and duplicate-execution tests pass

[ ] BigQuery and logging evidence is complete

[ ] Rollback procedure was tested

Approval gate Reviewer decision: [ ] Approve controlled implementation [ ] Request changes [ ] Reject. Reviewer: ____________________ Date: ____________________ Evidence reference: ____________________

# Phase 5: Implementation

## Deployment sequence

# Validate
chmod +x scripts/*.sh
./scripts/phase5-validate.sh

# Provision
terraform -chdir=terraform init
terraform -chdir=terraform plan -out=phase5.tfplan
terraform -chdir=terraform apply phase5.tfplan

# Connect and build
gcloud container clusters get-credentials vertex-agent-lab --zone us-central1-a --project class-6-5-tiqs
./scripts/build-phase5-images.sh
./scripts/install-falco.sh

# Deploy in fail-closed mode
./scripts/deploy-phase5.sh

# Verify
./scripts/smoke-test-metrics.sh
./scripts/test-phase5-governance.sh
./scripts/test-pipeline.sh

# Review and sign a pending approval when required
./scripts/review-phase5-approval.sh approve analyst@example.com "Approved after evidence review"

## Operational handoff

| Handoff item | Operational requirement |
| --- | --- |
| Owner | AI Platform / Cloud Security engineering |
| Primary runbook | docs/RUNBOOK.md |
| Runtime health | Pod probes, PodMonitoring, Cloud Monitoring, and Pub/Sub backlog alerts |
| Security evidence | Cloud Logging, BigQuery, Firestore state, release-evidence artifacts |
| Incident path | Inspect agent logs, Pub/Sub debug subscriptions, and the DLQ before replaying or modifying messages |
| Emergency stop | Set AUTOMATION_MODE and EXECUTION_MODE to disabled; rotate MCP credentials if needed |
| Change control | Pull request validation, signed release evidence, protected production environment, reviewed digest deployment |

# Appendix A: Major component summary

| Component | Role |
| --- | --- |
| GKE and Workload Identity | Runs isolated Kubernetes workloads and maps service identities without static cloud keys. |
| Artifact Registry | Stores immutable container images and release digests. |
| Pub/Sub | Connects every security pipeline stage with retries and dead-letter handling. |
| Event Aggregator | Normalizes Falco, Trivy, Prowler, Cloud Logging, and SCC findings. |
| Observer Agent | Validates and enriches incoming findings. |
| Correlation Agent | Combines related findings into incidents and stores correlation state in Firestore. |
| IR Analyst Agent | Uses Gemini to assist explanation, confidence, severity, and response recommendation. |
| Governance Agent + OPA | Converts an AI recommendation into a deterministic authorization decision. |
| Cloud KMS + Approval Agent | Signs and validates human approval while enforcing expiry, binding, and replay controls. |
| Remediation Agent | Acts as the policy-enforcement point and independently verifies authorization. |
| MCP Gateway | Provides an nginx mTLS boundary that accepts only the Remediation Agent certificate. |
| MCP Server | Executes a small set of validated, RBAC-scoped Kubernetes tools. |
| Reporting Agent | Creates the final incident report and optional Slack/Jira delivery. |
| Firestore | Stores correlation, approval, and execution state. |
| BigQuery | Stores durable governance and audit evidence. |
| Managed Prometheus | Collects metrics and supports dashboarding and alerts. |
| Falco / Trivy / Prowler | Provide runtime, image/configuration, and cloud-posture findings. |
| GitHub Actions / WIF | Validates and releases the platform without a long-lived service-account key. |
| Syft / Cosign | Generate SBOMs, sign images, attach attestations, and verify release identity. |

## Real-world relevance

The project models how a modern enterprise security operations or AI platform team can use AI to accelerate incident triage without allowing the model to authorize itself. The same control objectives appear in real systems: event buses, agent runtimes, policy decision points, cryptographic approvals, SOAR-style execution workers, tool gateways, identity federation, observability, evidence retention, and signed software releases. A Fortune 500 implementation would add regional resilience, production PKI, admission-time trust enforcement, multi-tenancy, formal SLOs, enterprise SIEM/SOAR integration, red-team evaluation, and organizational change management.

Enterprise application and compensation outlook. In a Fortune 500 environment, this platform would operate between cloud-security telemetry and the company's incident-response ecosystem: it would normalize findings, correlate related signals, use AI to accelerate analyst decisions, enforce deterministic policy and signed approvals, execute only narrowly authorized Kubernetes remediation, and preserve evidence for audit, compliance, and post-incident review. In California's July 2026 market, current postings for comparable work include NVIDIA Senior AI Platform Engineer base ranges of $184,000-$287,500 at Level 4 and $224,000-$356,500 at Level 5, while Walmart principal cloud and AI platform roles list $143,000-$286,000; based on those published ranges, an experienced Senior AI Platform Engineer with a DevSecOps and cloud-security background could reasonably target approximately $185,000-$290,000 in base salary, and a Principal or Staff-level engineer approximately $225,000-$356,000 or more, with bonus and equity potentially raising total annual compensation into roughly the $250,000-$450,000+ range depending on employer, location, experience, and organizational scope.

## Thirty-second elevator speech

Professional project introduction I built a governed, multi-agent security automation platform on Google Kubernetes Engine. It collects and correlates cloud and runtime findings, then uses Gemini to help analysts understand incidents. The key distinction is that AI never directly controls the environment: OPA policy, Cloud KMS-signed human approval, Firestore replay controls, mTLS, MCP, and Kubernetes RBAC independently govern every action. I also implemented observability, vulnerability scanning, SBOM generation, keyless image signing, and immutable releases, demonstrating cloud engineering, Kubernetes, DevSecOps, security governance, and responsible AI integration.

# Appendix B: Reusable Cursor AI Plan Mode prompt

You are acting as Cursor AI in PLAN MODE. Follow this workflow:

PHASE 1 - CLARIFICATION
Ask only the minimum technical questions needed to clarify scope, environment, existing files, security requirements, success criteria, blockers, and dependencies. Do not write code.

PHASE 2 - RESEARCH
Inspect the Phase 5 GKE agentic-security repository, identify the exact files and components affected, map dependencies, and identify risks or conflicts.

PHASE 3 - PLAN GENERATION
Create a detailed Markdown plan containing:
1. Overview and summary
2. Updated file structure
3. Step-by-step checklist with exact file references
4. Dependencies and prerequisites
5. Potential issues and mitigations
6. Testing strategy
7. Success criteria
8. Next steps
Also include time estimate, complexity rating, security/compliance considerations, multi-environment differences, and rollback strategy.

PHASE 4 - REVIEW
Ask for approval and do not implement until the plan is approved.

PHASE 5 - IMPLEMENTATION
After approval, generate complete files, configuration, tests, documentation, and deployment instructions. Preserve fail-closed defaults and do not enable controlled remediation without explicit approval.

MY REQUEST:
[Describe the Phase 5 change, bug fix, deployment, refactor, or new feature here.]

## Final review note

Current recommendation Use this document as the planning and review record. Use README.md for the recruiter-facing overview and docs/RUNBOOK.md for exact deployment and operational commands. The next technical milestone is a live fail-closed deployment followed by governance, approval, evidence, and rollback validation.